## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | 2225-swen-261-06-a-scrumblebees
Testing Team Name | 2225-swen-261-06-h-quackers

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a buyer I want to see a list of products so that I choose what to purchase. | Given that I am on the e-store site when I am not on the Products page then I must see a means to navigate to the Products page. | Pass | KA;03/15; | Pass | AL 04/04
| Given that I am not on the Products page when I choose the Products page then I am taken to the Products page. | Pass | KA;03/18; | Pass | AL 04/04
| Given that I am on the Products page when there are no products in the inventory I see a message indicating that that there are no products available. | Fail | KA;03/18;no messages displayed | Pass | AL 04/04
| Given that I am on the products page when there are products in the inventory then I see each product and short description. | Pass | KA;03/19; | Pass | AL 04/04
| Given that I am on the products page when there are products in the inventory then I see a means to add each product to my shopping cart. | Pass | KA;03/19; | Pass | AL 04/04
As a User I want to be able to log out of my account so that other users can log in on my device. | GIVEN I as a User am logged in WHEN I press the logout button THEN I am logged out, and can no longer view information pertaining to my account or features only available to logged in users | Pass | PN;03/17; | Pass | AL 04/04
As an Administrator I want to be able to log into my Administrator account so that I can manage the website. | Given I am on the login page WHEN I enter my admin credentials, THEN I should be logged in to the e-store as the administrator. | Pass | PN;03/17; | Pass | AL 04/04
| Given I am on the login page WHEN I enter invalid (admin) credentials, THEN I should be given a helpful error message and allowed to reenter credentials immediately. | Pass | PN;03/17; | Pass | AL 04/04
As an owner I want a button to update the product description for a products so that I can update the description of the products. | **Given** I am an admin, **when** I visit the edit page for a product **then** I expect to be able to edit the product's name, price, description, image, tags, and stock. | Pass | PN;03/18; | Pass | AL 04/04
| **Given** I am a customer, **when** I try to visit the edit page for a product **then** I will be redirected to the home page. | Pass | PN;03/18; | Pass | AL 04/04
| **Given** I am not logged in, **when** I try to visit the edit page for a product, **then** I will be redirected to the home page. | Pass | PN;03/18; | Pass | AL 04/04
As an Administrator I want to add new Items to the inventory so that I can expand my Item listings. | **Given** I am an admin, **when** I visit the add product page **then** I expect to be able to enter details for a product's name, price, summary, image, tags, and stock quantity. | Fail | KA;03/20; no option to enter images | Pass | AL 04/04
| **Given** I have populated the required fields **when** I click the add button, **then** the item will be added to the catalog. | Pass | KA;03/20; | Pass | AL 04/04
| **Given** I am a customer, **when** I try to visit the add product page **then** I will be redirected to the home page. | Pass | RW;03/20; | Pass | AL 04/04
| **Given** I am not logged in, **when** I try to visit the add product page **then** I will be redirected to the home page. | Pass | RW;03/20; | Pass | AL 04/04
| **Given** that I have entered all required fields, **when** I click the add button, **then** the form should clear to allow me to add another item. | Pass | RW;03/20; | Pass | AL 04/04
As a Customer I want to be able to log into my Customer account so that I can buy Items. | GIVEN I have typed a valid username into the username box WHEN I press the login button THEN the site will log me in and display features only available to logged in users. | Pass | NL; 03/19; | Pass | AL 04/04
| GIVEN I have typed an invalid username into the username box WHEN I press the login button THEN the site will display an error message notifying me that the username is invalid. | Pass | NL; 03/19; | Pass | AL 04/04
As a Customer I want to use a search bar so that I can search for specific Items. | GIVEN I am entering input to the search bar WHEN my input matches part of an item's name THEN that item should appear in the search results below the search bar. | Pass | NL; 03/15; | Pass | AL 04/04
As an Administrator I want to remove products from the inventory so that I can consolidate my Item listings. | **Given** I clicked delete product, when I'm in the dashboard, the product should be removed from the inventory | Fail | NL;03/19; | Pass | AL 04/04
As a Customer I want to view the entire catalog so that I can choose what to purchase. | **Given** I am on the homepage **when** scroll through the page **then** I expect to see a grid list of products. | Pass | RW;03/19; | Pass | AL 04/04
| GIVEN I enter the website WHEN I am starting the website THEN I expect to see the grid list of products | Pass | RW;03/19; | Pass | AL 04/04
| GIVEN I complete login authentication WHEN I attempt to login from the home page THEN it should take me back to the home page (grid list) | Pass | NL;03/19; | Pass | AL 04/04
As a Customer I want to add items to my shopping cart so that I can choose Items to purchase. | **Given** I am looking at a product description **when** I press "Add to Cart" button **then** the product should be added to the cart. | Pass | NL;03/20; | Pass | AL 04/04
| **Given** I am looking at a product description **when** I press "Add to Cart" button and the product already exists in it **then** the product counter should be incremented by 1. | Pass | KA;03/20; | Pass | AL 04/04
As a Customer I want to remove items from my Shopping Cart so that I can choose not to purchase it. | **Given** I am looking at my shopping cart **when** I press the "Remove" button **then** the product should be removed from the cart. | Pass | PN;03/20; | Pass | AL 04/04
As a Customer, I want to be able to see an items stock as ‘in stock’, ‘low on stock’, or ‘out of stock’ so that I can know when there is a sense of urgency | **Given** I am viewing an item's details **when** the item is in low stock, **then** I should see a message/tag in the details that says "Low on stock." |  |  | Pass | AL 04/04
| **Given** I am viewing an item's details **when** the item is in high stock, **then** I should see a message/tag in the details that says "In stock." |  |  | Pass | AL 04/04
| **Given** I am viewing an item's details **when** the item is out of stock, **then** I should see a message/tag in the details that says "Out of stock." |  |  | Pass | AL 04/04
As an ADMIN I want to be given a CONFIRMATION POPUP WHEN I DELETE A PRODUCT so that I don’t accidentally delete a product | **Given** I'm on the admin dashboard **when** I press the 'remove' button next to the product **then** I am presented with a confirmation popup |  |  | Pass | AL 04/04
| **Given** I'm looking at the confirmation popup **when** I press the 'confirm' button **then** the popup closes and the product is deleted |  |  | Pass | AL 04/04
| **Given** I'm looking at the confirmation popup **when** I press the 'cancel' button **then** the popup closes and the product is not deleted |  |  | Pass | AL 04/04
As a customer I want to be able to see the product images so that I can browse through the products better | **Given** the app is open **when** I scroll through the catalog **then** I should be able to see the products with images in tiles |  |  | Pass | AL 04/04
As a Customer I want to view an individual item’s listing to learn more details of the item. | GIVEN I am logged in as a customer WHEN I view an item listing page THEN I should see a picture of the item, a text description of the item, and a button to add the item to my shopping cart |  |  | Pass | AL 04/04
| GIVEN I am not logged in WHEN I view an item listing page THEN I should see a picture of the item, a text description of the item, and a button to log in to add the item to my shopping cart |  |  | Pass | AL 04/04
As a Customer I want to write a review and give a star rating so that I can share my current level of satisfaction. | **Given** I've purchased the product **when** I visit the product listing **then** I'm presented the option to leave a review |  |  | Pass | NL 04/06
| **Given** I've already left a review on a product **when** I visit the product listing **then** I'm not presented the option to leave a review |  |  | Pass | NL 04/06
| **Given** I'm given the option to leave a review **when** I press the 'submit review' button **then** the reviews page is updated along with the product's average rating |  |  | Pass | NL 04/06
| **Given** I'm a customer who has not left a review for the item yet, **when** I scroll to the reviews section of the product listing, **then** I should be presented with a form with a text box to write my review, and a UI element that lets me select a star rating for the review. |  |  | Pass | NL 04/06
| **Given** I am a customer writing a review, **when** filled out the review form with a review and a rating, **then** a Submit Review button will become selectable. |  |  | Pass | NL 04/06
| **Given** I have filled out the review form, **when** I have clicked Submit Review, **then** the review will be submitted, and I will see my review added to the reviews list. |  |  | Pass | NL 04/06
As a Customer I want to check out so that I can purchase the items in my cart. | **Given** there are no items items in my cart **when** I go to click checkout **then** there will be no option. |  |  | Pass | AL 4/04
| **Given** there are items in my cart **when** I am looking below the cart contents **then** I will be presented with a summary of the subtotal, taxes, and total price of my order. |  |  | Pass | AL 4/04
| **Given** there are products in my cart **when** I click checkout **then** I will be brought to the checkout screen. |  |  | Pass | AL 4/04
| **Given** I have clicked checkout when there were products in my cart, **when** I am brought to the checkout view **then** I should see a stepper element at the top of the screen showing my check out progress, starting at Contact info. |  |  | Pass | AL 4/04
| **Given** I'm in checkout **when** I am on the contact info step, **then** I expect to be asked to enter my First and Last name, Phone number, and Email. |  |  | Pass | AL 4/04
| **Given** I am on contact section, **when** I enter all information, **then** I expect a button to become enabled which proceeds to the next section of the stepper: shipping address. |  |  | Pass | AL 4/04
| **Given** I have clicked the proceed button from Contact **when** I enter the shipping address stepper section, **then** I expect to be able to enter my Country, State, City, Zip code, Address Line 1, an optional address line 2, and optional apartment number. |  |  | Pass | AL 4/04
| **Given** I am on address section of stepper, **when**, I enter all valid information, **then** I expect to have the option to advance to the payment method section of the stepper. |  |  | Pass | AL 4/04
| **Given** I have clicked the button to advance to payment method section, **when**, I am taken to the payment method section, **then** I expect to be able to enter my credit card number, Name on Card, Expiration, and CVV code. |  |  | Pass | AL 4/04
| **Given** I am on the payment section, **when**, I have entered the valid payment information, **then** I expect to be able to click a button to continue to the order review section of the stepper. |  |  | Pass | AL 4/04
| **Given** I have clicked the button to proceed to order confirmation, **when**, I enter the order confirmation section, **then** I expect to see a breakdown of all my order information, including all form data and the items I will be purchasing, as well as a large "Place Order" button. |  |  | Pass | AL 4/04
| **Given** I all the data is correct, **when**, I click place order, **then** I expect to be taken to a confirmation screen that displays the success state of the order placement. |  |  | Pass | AL 4/04
As the estore owner I want to delete the reviews left by customers so I can maintain a positive environment in the estore owner | **Given** I can see the reviews written by the customer on a product **when** I click 'delete review' **then** the review is removed from the reviews page |  |  | Pass | NL 04/06
As a Customer I want to delete my reviews so that I have control over my voice. | **Given** I've left a review on a product **when** I click 'delete review' **then** the review is removed from the reviews page |  |  | Pass | NL 04/06